## Risk Register
Risk-Weighted Contingency Register — Made by Plan of Day · planofday.com/tools/construction-contingency-calculator
Expected value = probability × impact. Sum is a defensible contingency floor. Replace the example risks with your own.
Risk | Probability (%) | Impact ($) | Expected value ($) | Notes
Weather / lost days | 60 | 40000 | 24000
Subcontractor default | 15 | 120000 | 18000
Design change / RFI rework | 45 | 60000 | 27000
Material price escalation | 50 | 80000 | 40000
Unforeseen site condition | 30 | 90000 | 27000
EV contingency floor |  |  | 136000
Project value ($) | 4000000
Contingency % (floor ÷ project value) | 3.4
Note on D4: Computed — do not edit

## AACE bands & sources
AACE estimate-class contingency bands (class-typical ranges)
Class 5 — concept screening | 30–50%
Class 4 — study / feasibility | 20–35%
Class 3 — budget authorization | 10–20%
Class 2 — control / bid | 5–15%
Class 1 — check estimate | 3–10%
Method |  | Expected value = Σ (probability × impact). Cross-check the resulting % against your estimate class and project phase.
AACE RP 40R-08 / 44R-08 |  | Contingency estimating & risk analysis (expected value). https://web.aacei.org/resources/publications/recommended-practices
AACE RP 17R-97 / 18R-97 |  | Cost estimate classification.
ISO 31000 |  | Risk management principles. https://www.iso.org/iso-31000-risk-management.html
Live version |  | planofday.com/tools/construction-contingency-calculator