## Delay Log
Delay / Extension-of-Time Log — Made by Plan of Day · planofday.com/tools/schedule-delay
Log each critical-path delay, classify it, and price the exposure (delay days × daily cost). Eichleay HOOH is on the next tab.
Delay event | Start (day #) | End (day #) | Delay days | Excusable? | Compensable? | Concurrent? | Daily cost ($) | Exposure ($)
Owner design change | 40 | 58 | 18 | Yes | Yes | No | 4500 | 81000
Unusual weather | 62 | 70 | 8 | Yes | No | No | 3800 | 30400
Late owner approval | 88 | 96 | 8 | Yes | Yes | Yes | 5200 | 41600
TOTAL exposure | [7 empty] | 153000
Note on D4: Computed — do not edit
Note on I4: Computed — do not edit

## Eichleay & sources
Eichleay home-office overhead (federal 3-step)
Total home-office overhead in contract period ($) | 1800000
Billings on the delayed contract ($) | 6000000
Total firm billings, same period ($) | 24000000
Days of contract performance | 300
Days of compensable (owner-caused) delay | 30
Allocable overhead = HOOH × (delayed ÷ total billings) | 450000
Daily overhead rate = allocable ÷ days of performance | 1500
Recoverable overhead = daily rate × compensable days | 45000
Eichleay |  | Federal remedy for unabsorbed home-office overhead; requires a sole owner/government-caused delay with no concurrency (Eichleay Corp., ASBCA 1960; Fed. Cir.).
SCL Protocol |  | Society of Construction Law Delay & Disruption Protocol. https://www.scl.org.uk/
AACE RP 29R-03 |  | Forensic schedule analysis. https://web.aacei.org/resources/publications/recommended-practices
Live version |  | planofday.com/tools/schedule-delay