## EVM Tracker
Earned Value (EVM) Tracker — Made by Plan of Day · planofday.com/tools/schedule-performance
Replace the example rows with your activities. The shaded columns (PV → VAC) are formulas and recompute automatically.
Activity | BAC ($) | % Complete | Planned % | Actual Cost ($) | PV ($) | EV ($) | CV ($) | SV ($) | CPI | SPI | EAC ($) | VAC ($)
Foundations | 200000 | 100 | 100 | 195000 | 200000 | 200000 | 5000 | 0 | 1.0256 | 1 | 195000 | 5000
Structure | 500000 | 60 | 70 | 320000 | 350000 | 300000 | -20000 | -50000 | 0.9375 | 0.85714 | 533333.3333 | -33333.3333
MEP rough-in | 300000 | 30 | 40 | 100000 | 120000 | 90000 | -10000 | -30000 | 0.9 | 0.75 | 333333.3333 | -33333.3333
Finishes | 250000 | 5 | 10 | 12000 | 25000 | 12500 | 500 | -12500 | 1.0417 | 0.5 | 240000 | 10000
TOTAL | 1250000 |  |  | 627000 | 695000 | 602500 | -24500 | -92500 | 0.96093 | 0.86691 | 1300829.8755 | -50829.8755
Note on F4: Computed — do not edit
Note on G4: Computed — do not edit
Note on H4: Computed — do not edit
Note on I4: Computed — do not edit
Note on J4: Computed — do not edit
Note on K4: Computed — do not edit
Note on L4: Computed — do not edit
Note on M4: Computed — do not edit

## Sources & method
Sources & method
Method | Earned value management: PV = BAC × planned %, EV = BAC × % complete, AC = actual cost. CV = EV − AC, SV = EV − PV, CPI = EV ÷ AC, SPI = EV ÷ PV, EAC = BAC ÷ CPI, VAC = BAC − EAC.
PMI PMBOK Guide | Earned value / performance measurement. https://www.pmi.org/pmbok-guide-standards
ANSI/EIA-748 | Earned Value Management System standard.
Live version | planofday.com/tools/schedule-performance · planofday.com/tools/estimate-at-completion